Team 7 — please read carefully.

1. Locked project scope (final)

Research question:
How quickly do Nasdaq MPID-attributed liquidity providers react (via add / cancel / replace) to external price shocks, using CME ES trade events as the stimulus?

Design choices (frozen):

- Stimulus: CME ES trade messages only (LastTradeMsg)

- Response: Nasdaq XNAS MPID add / cancel / replace events

- Latency metric:
Time from ES trade timestamp → first subsequent MPID action

- Aggregation:

  - Per MPID

  - Per hour / per day

  - Distributional analysis (histograms, summary stats)

- Scope control:

  - Limit to top MPIDs by activity

  - Limit to top symbols (e.g., QQQ, IWM, TSLA)

Anything outside this does not get worked on.

2. Required deliverables by Monday 7am

Code / data

- CME ES trades parquet (clean, minimal)

- Nasdaq MPID event parquet (adds/cancels/replaces)

- Joined latency table:

- es_trade_time_ns | mpid | symbol | event_type | latency_ns

Analysis

- Latency histograms

- Per-MPID summary table (mean / median / tails)

- Time-of-day effects (hourly)

Write-up / slides

- Problem statement

- Data & methodology

- Results

- Interpretation + limitations

3. Task assignments (parallel, non-overlapping)

CME ES trade extraction

Owner: Chintan
Deadline: Tonight

- Extract ES trades only

- Output fields:

- trade_time_ns | trade_px | trade_sz

- At least one full trading day (more if feasible)

Done = parquet file ready to join

Nasdaq MPID event pipeline

Owner: Ivaylo
Deadline: Tonight

- XNAS only

- Add / Cancel / Replace only

- Required fields:

- event_time_ns | mpid | symbol | side | price | size | event_type

- Limit symbol universe

Done = parquet file ready for latency join

Latency join + analytics

Owner: Harsh (team lead)
Deadline: Tomorrow morning

- For each ES trade, find first subsequent MPID event

- Compute latency in nanoseconds

- Aggregate per MPID / per hour

- Generate plots + tables

Done = figures and tables usable in slides

Narrative & interpretation

Owner: All (coordinated by Harsh)
Deadline: Sunday

- Why ES → Nasdaq is economically meaningful

- What latency differences imply

- Explicit limitations (clock sync, MPID aggregation, observability)

4. Checkpoints

- Tonight: Both data pipelines complete

- Tomorrow (midday): Latency join working, first plots

- Sunday: Final analysis + write-up

- Monday 7am: Submission-ready

5. Ground rules

- No new scope unless it replaces existing work

- Post immediately if blocked

- Silence = not progressing

- This is now an execution problem, not an ideation problem

Execute on this plan and you will have a strong, defensible project.